## Sheet1
Tech Stack | Epic | Story | Task | Resource | Progress | Blockers
WSO2 APIM | WSO2 APIM Automation Workflow | Dev Rollout | API Export | Kavindu | Done
|  |  | API Import | Kavindu | Done
|  |  | Update API Endpoints | Kavindu | Done
|  |  | Deploy API to Gateway | Kavindu | Done
|  |  | Create Applications | Kavindu | Done
|  |  | Create Subscriptions | Kavindu | Done
|  |  | Approve Subscriptions | Kavindu | Done
|  | QA Rollout | API Export | Kavindu | In-Progress
|  |  | API Import | Kavindu | In-Progress
|  |  | Update API Endpoints | Kavindu | In-Progress
|  |  | Deploy API to Gateway | Kavindu | In-Progress
|  |  | Create Applications | Kavindu | In-Progress
|  |  | Create Subscriptions | Kavindu | In-Progress
|  |  | Approve Subscriptions | Kavindu | In-Progress
|  | Production Rollout | API Export | Kavindu
|  |  | API Import | Kavindu
|  |  | Update API Endpoints | Kavindu
|  |  | Deploy API to Gateway | Kavindu
|  |  | Create Applications | Kavindu
|  |  | Create Subscriptions | Kavindu
|  |  | Approve Subscriptions | Kavindu
| WSO2 APIM Patch Update Automation | Dev Rollout | Check Update Level | Kavindu | In-Progress
|  |  | Apply Security Update | Kavindu
|  |  | Rollback Security Update | Kavindu
|  | QA Rollout | Check Update Level | Kavindu
|  |  | Apply Security Update | Kavindu
|  |  | Rollback Security Update | Kavindu
|  | Production Rollout | Check Update Level | Kavindu
|  |  | Apply Security Update | Kavindu
|  |  | Rollback Security Update | Kavindu
WSO2 IAM | WSO2 IAM Patch Update Automation | Dev Rollout | Check Update Level | Kavindu | In-Progress
|  |  | Apply Security Update | Kavindu
|  |  | Rollback Security Update | Kavindu
|  | QA Rollout | Check Update Level | Kavindu
|  |  | Apply Security Update | Kavindu
|  |  | Rollback Security Update | Kavindu
|  | Production Rollout | Check Update Level | Kavindu
|  |  | Apply Security Update | Kavindu
|  |  | Rollback Security Update | Kavindu